## Slide 1
Client: Victor Allen
Project: Construction of Small Office
Date: 2/14/2024 Revision:
Ideal State
Gap to be Corrected
Problem/Project Statement
Major Risks Identified
Current State
Case for Change
Key Business Assumptions
Performance Criteria | Current | Target
Avg call Duration time | 24 hrs. | 48 hrs
Avg time on hold | 1 hr | 30min.
Worker Satisfaction rating | 25% | 50%
Scope Statement
1
3
4
2
Key Project Milestones | Date
Office facility planning and design | 06/03/24
Procurement of materials, equipment, and labor | 06/17/24
Commencement of construction | 07/01/24
Completion of structural construction | 10/14/24
Installation of plumbing, electrical, and HVAC | 11/15/24
Installation of security systems and technology | 01/02/25
Completion of interior finishing and landscaping | 03/05/25
Final inspection and handover to the client | 05/29/25
Prelim IRR = 15.67%.
Project Charter
Constructing a new office facility for 80 employees to address space limitations, improve efficiency, and create a conducive work environment.
Total Estimated Project Cost = $8M
Delays in permits and approvals, exacerbated by weather disruptions.
Challenges coordinating contractors, with potential labor shortages and budget overruns due to unforeseen site conditions.
Client approval for proposed design and specifications.
Availability of necessary resources, materials, and labor for construction.
Compliance with all regulatory requirements and building codes.
Approval | Init | Date
Client: Victor Allen |  | 
Platform Manager/Director: |  | 2/14/2024
This project entails comprehensive planning, design, and engineering for the construction of a new office facility capable of accommodating approximately 80 people. The facility will incorporate essential amenities such as storage, multiple doors, call center, bathroom facilities, conference rooms, patio, lunchroom, landscaping, and security systems. Coordination for permits, compliance with building codes, and handover to the client are integral parts of the scope. The project excludes ongoing maintenance and furnishing post-construction.
The objective of this project is to address these challenges by constructing a new office facility capable of accommodating approximately 80 people. This move is crucial for improving operational efficiency, fostering collaboration among team members, and providing a conducive work environment that aligns with the organization's growth trajectory and strategic objectives.
Organizational Impacts
To bridge the gap from our current state of operating at full capacity in a leased office to the ideal state of constructing a new facility for 80 employees, several steps need to be taken. Firstly, we will identify suitable locations and secure funding and approvals. Then, detailed plans will be developed, and necessary resources will be procured for construction. Finally, a smooth transition to the new facility will be facilitated, aiming to enhance efficiency and create a conducive work environment.
Constructing a new office facility with modern amenities is essential to address existing deficiencies, foster employee productivity, and support organizational growth and success.
Major Risks Identified
Operating in a leased office at full capacity, forcing 40 employees to work remotely due to space constraints and rising leasing costs.
Coordination with city authorities, contractors, and client representatives, alongside effective communication among project team members, to ensure project success.

## Slide 2
Excluded from Scope
Included in Scope
Project Charter
5
6
Furnishing and cubicles for the office space.
Ongoing maintenance and operation of the office facility post-construction.
Detailed planning and design of the office facility, including architectural and engineering drawings.
Procurement of necessary materials, equipment, and labor for construction.
Construction of the office facility according to approved plans and specifications, ensuring compliance with building codes and safety standards.
Installation of plumbing, electrical, HVAC systems, security cameras, door swipe locks, and technology equipment as per project requirements.
Coordination with city authorities to obtain permits and approvals for construction activities.
Testing and commissioning of all installed systems to ensure proper functionality and safety.
Handover of the completed office facility to the client, including any required documentation and training for facility management.
Design and implementation of the lunchroom, ensuring it meets the needs of employees and complies with health and safety regulations.
Allocation and layout planning for the number of offices, considering the organization's operational requirements and workforce projections.
Provision of adequate parking facilities, including accessible parking and bicycle storage, to accommodate employees and visitors.
Integration of landscaping elements to enhance the aesthetic appeal and sustainability of the surroundings.
Implementation of a comprehensive security system, including access control measures and surveillance cameras, to ensure the safety and security of the facility.
Establishment of a dedicated data room with proper security and climate control measures to house the organization's IT infrastructure.
Collaboration with architects, engineers, and stakeholders to optimize space utilization, ergonomic design, and sustainability practices throughout the project.

## Slide 3
Excluded from Scope
Included in Scope
Project Charter
5
6
Implementation of energy-efficient solutions and sustainable building practices to minimize environmental impact and reduce long-term operational costs.
Incorporation of flexible workspace designs to accommodate evolving needs and promote collaboration among employees.
Integration of smart building technologies for efficient energy management, building automation, and remote monitoring.
Provision of amenities such as break areas, meeting rooms, and recreational spaces to enhance employee well-being and productivity.
Consideration of accessibility requirements to ensure the office facility is inclusive and accessible to individuals with disabilities.
Collaboration with interior designers to create a cohesive and aesthetically pleasing interior environment that reflects the organization's brand and values.
Implementation of soundproofing measures to minimize noise disturbances and create a conducive work environment.
Incorporation of sustainable transportation options, such as electric vehicle charging stations and bike-sharing programs, to promote alternative commuting methods.
Integration of green building features, such as renewable energy systems, rainwater harvesting, and green roofs, to enhance environmental sustainability and resilience.
Provision of adequate storage solutions and organizational systems to optimize space usage and facilitate efficient workflow.
Implementation of emergency preparedness measures, including evacuation plans, fire suppression systems, and emergency lighting, to ensure the safety of occupants during unforeseen events.